## 18.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | Waited for the increment detais. | Waited for the increment detais. | waited for the increment details | waited for the increment details.
What is your plan for today? | I will work on the coding part once I received the design for the interface. | I will work on the table design part of the registration page. | I was working on the coding part with rahela together. | I will work on the social media buttons design of the page.
What are the obstacles you have faced? | I should contact the product owner on how to validate the form. | no issue yet. | issues with declaring some values | things were clear.

## 19.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | connecting social media icons to the required pages. | the tables were organized and professional looking. | coded the form when the design was received. | I am almost done with the design of social media buttons
What is your plan for today? | error messages functions and agreement line validating. | designing the overall registration form | I will write functions to the buttons | to wrap things up and have a complete interface.
What are the obstacles you have faced? | the communication was a little extra | organizing the entry boxes. | there wasn’t any specific problem | reaching out to product owner to cooperate in the design process

## 20.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | validated the functions and connected the page with the database. | designed the form along with the suitable theme and colors to be related with others, | wrote the functions to make it fully function page. | completed the job seeker registration page. And started creating a dashboard for the job seeker.
What is your plan for today? | waiting for the design and will work on 1 tab. Plus I will work on logout buttom. | I will work on the layour of the dashboard along with fonts and colors. | I will wait for the rest of the design and now will work on my profile tab. | I will work on overall view of the dashboard.
What are the obstacles you have faced? | dose of other work along with this. | finding suitable font and colors to match the pictures is still an issue. | no issue yet. | the arrangements of the tabs for the job seeker page.

## 21.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | I worked on the my cart tab. And connect that to the jobs when its added. | designed the layout for the dashboard | declaring the functions of the tobs in job seeker view page. | organized few tabs and added pictures and fonts to it.
What is your plan for today? | will work on the next tabs upon receiving the design of it. | creating new images for the tab from scratch. | will work on the functions of the tabs | organizing the other tabs to have a complete interface.
What are the obstacles you have faced? | the design part made a little delay in our work | accepting eachother point of view and coming up with something mutual. | not so satisfied with the design of few tabs. | little communication and arguments over small details.

## 22.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | I worked on the approved application and need help tabs. | created new images for the icons. | I wrote the code for view jobs and update resume tabs and linked them to the next pasges. | made few changes as per upon the request.
What is your plan for today? | I will work on the rest of the tabs. | there was nothing left to do. | wrote all the functions for the tabs and completed the task. | ther overall view was looking good and our task was done
What are the obstacles you have faced? | things were moving smoothly | creating new images from scratch | virtual meetings. | no problem till now.

## 23.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | tabs were finished and the page was ready. | the design part for this specific increment was finished and I waited for the next task. | the overall fully function interface of the system is ready. | our task was finished
What is your plan for today? | I will wait for the design | working on the overall layout on how the page should look like | will start working once the design is received | working on the tables part of the page.
What are the obstacles you have faced? | I don’t have any issue. | coming up with something effective along with ahmad | there is no task so no obstacles. | having different ideas

## 24.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | waited for the design to start working on coding part. | the layout of the page was designed. | looking forward to have an appealing design. | placed the tables on the window along with the search bar.
What is your plan for today? | after receiving the design instantly starting work on the coding. | will work on the colors of the buttons | I will code the designed part | will work on the structure of the boxes.
What are the obstacles you have faced? | connection problem | there is no problem yet | no problem. | sizes of the box and fonts