## 25.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | worked on some of the tabs that was already designed. | Started with designing page of modify jobs and managment. | Finished the coding part for some of the tabs in the user view page | worked on the buttons.
What is your plan for today? | waiting for the designers to get done with the design and then will start coding it. | Working on desiging the modify job buttons and choosing colors | waiting to receive the designs and start working on those parts | working on the rest of the interface.
What are the obstacles you have faced? | no issue. | No obstacle so far. | Everything is well | things were clear.

## 26.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | some parts of the design were recieved and started work on it. | Finished desiging the modify jobs and buttons. | was waiting to receive the design to start working | finished the overall design of the interface
What is your plan for today? | i will work on the delete button and finish the connection with the database. | Started working on the managment table and were thinking about the colors for table that should it be simple or filled with colors. | I am working on the conding part of the Load button, hopefully will be done by today | helped faryal with the tasks.
What are the obstacles you have faced? | waiting for the design was a llittle time consuming. | No obstacle so far. | Nothing | things are fine

## 27.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | i m done with coding of delete button and the database connection for the page. | Worked on management table and finished that part. | I was working on the coding of the load button | gave some advices and helped faryal in the designing part.
increment 6 enja khalas mesha
What is your plan for today? | i will work on the add button and the rest of the page to get the page done. | Started working on search button and logout button since they are important for this page we could not decide where it should be located to not make this page look so confusing. Still working on that part and not done yet | I am working on the update button, hopefully will finish it by today | i will collaborate with faryal's task and will do things together.
What are the obstacles you have faced? | no obstacles and issues yet. | Location of search button and logout button. | nothing | no obstacle

## 28.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | i was done with the add button and the rest of the page coding. | Started working on design part of jop application management system and this page has a table which include job title job id and so on. | done with the load and update buttons in the job management page | collaborated in prototyping and designing with faryal.
increment 7 shro mesha ki tab view job da page job seeker ast.
What is your plan for today? | i will be waiting for the design to be recieved from the designers. | Designed some parts of this application management system and still kot done | waiting to receive the design for the next increment and will start working on it as I receive it | will work as my teammate will require me to do so.
What are the obstacles you have faced? | no obstacles yet. | The table needed connection to database so for that reason we had to finish the design earlier. | nothing | no problem

## 29.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | was waiting for the design to get finalized. | We were working on desiging that page of application and not done yet. | nothing | designed the main interface.
What is your plan for today? | will start working on the application page layout coding | Yet we are working since we had less time for this yesterday due to discussions from other classes. | received the tables design and working on connecting them with the database and the other functionalities for those tables | i will work on the overall layout of the page and some buttons.
What are the obstacles you have faced? | i dont find it hard so no issue yet. | No obstacle yet | no obstacle | no problem.

## 30.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | done with the overall coding of the layout. | Finished the design for the some parts of this page of application and the developer has started working on the coding part of this and connecting this to database.) | finished the database part of the tables | designed the layout of the page but some parts are remaining.
What is your plan for today? | i will work on the 2 buttons which are apply and search. | Still working on the design part and we are about to finish this page since there is not much more left for desiging.. | Working on the functionality of the logout button in the page. | will help my teammate in the process.
What are the obstacles you have faced? | no problem for me. | No obstacle yet | nothing | no issues yet.

## 31.04.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | done with coding of the apply and search button and box | Finished the design part of this page | Finished the coding part for the functionality of the back button | helped in the process of the designing part along with fayral
What is your plan for today? | i will work on the apply page functionaities to connect it to the other page. | Were explaining that design for others and asking for their suggestions. | Working on the functionality of the logout button in the page. | i will work on the rest ppf theings that is eft.
What are the obstacles you have faced? | i dont have any issue regarding the task i did. | No obstacle | Nothing | no issue yet.