## 1.04.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | the functions for the apply button is done. | Since we were working on part of design and it was completed so we had nothing more to do. |  | Almost completed.
What is your plan for today? | i will work on the rest of the page and try to code the design of it. | If anyone has suggestion for the design so they can let us know otherwise we are done with the part of designing this increment. | will work on the rest of the page the parts that are left. | Open to suggestions.
What are the obstacles you have faced? | no issues yet.. | No obstacle yet | no problem. | Nothing special.

## 2.04.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | the functionalities are done and the increment was push. | Started designing and helping with code part of new increment of this week | worked on the remaining part of the increment. | Figured out the best suiting layout for this portion.
What is your plan for today? | i will work on the apply button page upon recieving the design form the designers | Since this new increment has less work for designing part so we will finish it by tomorrow. | i will wait for the design to recieve it. | It will be completed soon.
What are the obstacles you have faced? | i dont have any problem with anything yet. | No obstacle | nothing. | We did not face any obstacle.

## 3.04.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | i was waiting for the design to recieve it. | Finished with the part of designing of this increment | waited for the design. | Completed the design.
What is your plan for today? | i am going to work on the submit button and its functionalities. | Any new suggestions please let us know otherwise we are done. | i am going to work on the exit button and its functionalities. | All open to suggestions and changes in small details of the design.
What are the obstacles you have faced? | things are simple and easy. | No obstacle | no issue. | No really challenges faced.