## 11.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | after seeing the design. I started working on the coding part. | as we worked yesterday on design part and had our ideas shared. I come up with more specific layout for the page. | I worked on the buttons of the page. | I helped in the designing part and came up with appealing design.
What is your plan for today? | since I did some of the coding yesterday. Today im going to be done with it. | with the design in hand I prototype the page. | I wil work on the upper side of the page. | I will work on the paragraph text.
What are the obstacles you have faced? | Things were clear. So I didn’t face any issue. | currently I didn’t face any obstacle in the process. | there was no problem. | we are good to go ahead!!

## 12.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | i connect the main page to the admin login page. Where only validate admins can log in. | I worked on the design of user login page. | I worked on the user functionalities. | I work on the design of admin login page. I tried to customized the page clean and professional.
What is your plan for today? | once admin login is successful I will make it ti redirect it to the admin page. | working on the colors of the page. | I m going to code the layout of the user login page. | the rest of the page will be done.
What are the obstacles you have faced? | I didn’t face any problem. Fortunately. | I didn’t face any problem. If I had any problem I will share it with my team mates. | I didn’t find it hard. | a little bit sleepy and time due to the overdose of outside job.

## 13.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | connection with the database was successful. | the overall design for the user login page is done. | the layout for the user page is coded and some of the functionalities are coded as well. | the layout of the admin login page is fully designed.
What is your plan for today? | to push the code. | to hand the design to be coded. | the login button will be connected to the database. | scheming through the colors and overall pattern.
What are the obstacles you have faced? | not a specific problem | choosing color was problematic for the system. | I havent face any problem, | making the admin and user page kinda looking similar to eachother.

## 14.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | 2nd increment was successfully pushed | the design were given to the coders in order to code the page. | all the buttons were connected after giving the valid username and password user will go to the user view page. | the overall admin page design was eye capturing and clean as per expectations and meeting the requirement.
What is your plan for today? | brainstorming about the 3rd increment | finding pictures for the icons | helping in designing the view of the admin page. | working on the layout of the admin view page.
What are the obstacles you have faced? | python is easy and system is simple. So I didn’t face any problem. | no problem yet! | working in a team doesn’t give so much problem. | coming up with 1 solid idea

## 15.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | choose few layout designs for the tabs. | since there was not high resolution pics according to our need finded tools to create icons. | coded half of the design layout | created the design layout of the admin view page.
What is your plan for today? | planning to code the specific choosen theme | will try to create image using different tools such as adoba | code the tabs of the page | working on the icons
What are the obstacles you have faced? | electricity issue and charge | finding proper photoes according to system | no problem yet | creating new icons as an image

## 16.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | coded the design layout of the admin view page | created simple icons for the tabs | upon having the icons created coding the rest of the code | new icons were created according to the taba name
What is your plan for today? | the code will be ready to push | fonts and colors of the overall system | the rest of the code is going to be delivered | design the little detais
What are the obstacles you have faced? | receiving the design late | so much lengthy | things were clear and professional | not a problem

## 17.03.2021
Daily Scrum Meeting Report
| Rahela Jawadi | Faryal Fazel | Murtaza Mohammadi | Ahmad Bayat
What did you do yesterday? | the code for the layout of the page is ready. | the fonts and the colors of the system was determined. | the code is ready to be delivered | designing the little details in the icons of the tabs
What is your plan for today? | waiting for next increment | waiting for the next inremenet | waiting for the next increamnt | waiting for the next increment
What are the obstacles you have faced? | the page was simple and was not problematic that’s why we are done ahead of the time. | a little more hardwork | internet issues | creating icons were taking a lot of the time